## agile - sprint planni
Backlog
Name | Long Text | Status | MVP | Dependent On | Priority | Estimated Effort
Split Creation Basic UI | Create a Split Cancel Split in creation Add Total Expense Display Unallocated Balance (Remaining) | Not Started | YES |  | High | 2
Split Creation Basic Send Communcation | Add Friend/Group to a Split Send request to split members | Not Started | YES | Friends List Basic View, Friend Request Basic Send, Friend Request Basic Accept, Groups List Basic View, Group List Basic Creation, Group Request Basic Accept | High | 2.5
Split Creation Basic Receive Communcation | Allow for friend/group to verify request and notify via in-app notification Save request as a verified split request to server | Not Started | YES | Split Creation Basic Send Communcation, Split Request Basic View and Accept | High | 2.5
Friends List Basic View | View all friends Remove friends | Not Started | YES |  | High | 1
Friend Request Basic Send | Send friend requests Display all pending friend requests | Not Started | YES |  | High | 2.5
Friend Request Basic Accept | Allow user to accept or deny pending friend requests | Not Started | YES | Friend Request Basic Send | Medium | 1
Groups List Basic View | View all groups Display members | Not Started | YES |  | High | 1.25
Group List Basic Creation | Create groups Delete groups | Not Started | YES |  | High | 2
Group Request Basic Accept | Allow user to accept or deny pending group requests | Not Started | YES | Group List Basic Creation | Medium | 1
Payment Basic View | Select expense(s) to pay back Display owed balance | Not Started | YES | Expense Organization/History Basic View | High | 2
Payment Basic Payment and Payment Integration | Choose amount to pay back Choose payment method via selected payment integration Confirm payment | Not Started | YES | Payment Basic View, Account Basic Change Settings | High | 3.5
Profile Page Basic View | Display account information (name, email, phone, profile picture) | Not Started | YES |  | Medium | 1
Account Basic Change Settings | Change account information Add/Delete/Change Payment information (Credit/Debit cards, Venmo, etc.) | Not Started | YES | Profile Page Basic View | Medium | 1.5
Expense Organization/History Basic View | View history of all incoming/outgoing expenses ("I owe you"/"You owe me") | Not Started | YES | Split Creation Basic Receive Communcation, Split Creation Basic Send Communcation | High | 3
Expense Actions Basic Expense Forgiveness/Cash Payments | Forgive expense Manually apply favors/cash payments to outgoing expense | Not Started | YES | Expense Organization/History Basic View | Medium | 1.5
Split Request Basic View and Accept | Display all pending split requests Allow user to accept or deny pending split requests | Not Started | YES | Split Creation Basic Send Communcation | High | 2
Split Creation Options | Add payment category (food, rent, trips, other) Add options for Equal Split/Percent Split/Custom Split/Mix and Match Split Add periodic options for recurring payments | Not Started | NO | Split Creation Basic UI, Split Creation Basic Send Communcation, Split Creation Basic Receive Communcation | Medium | 5
Friends/Groups Display Expense Information | Display friend expense information Display group expense information | Not Started | NO | Friends List Basic View, Expense Organization/History Basic View, Groups List Basic View | Medium | 3
Friend/Group Search Bar | Search for friends/groups by name/email/phone number | Not Started | NO | Friends List Basic View, Friend Request Basic Send, Groups List Basic View, Group List Basic Creation | Low | 2
Friend Request – Search for people by different methods | Search via name/email Search via phone contacts | Not Started | NO | Friend Request Basic Send, Group List Basic Creation, Account Basic Change Settings | Medium | 3.5
Friend Request Notification | Show indicator when there are pending friend requests | Not Started | NO | Friend Request Basic Accept, Friend Request Basic Send, Friends List Basic View | Low | 2.5
Payment Pay from Friend List | Select friend to pay back from friend list/IOU list | Not Started | NO | Payment Basic View, Payment Basic Payment and Payment Integration, Friends List Basic View, Expense Organization/History Basic View | Low | 2
Expense Display History Action | Display payment history for the expense | Not Started | NO | Expense Organization/History Basic View | Medium | 2
Change Password and Accessibility Settings | Change password Change language Light/Dark Mode | Not Started | NO |  | Low | 2
Change Notification Content Settings | Toggle whether to see incoming payment notifications Toggle friend request notification Toggle pending split request notification | Not Started | NO | Split Creation Basic Send Communcation, Split Creation Basic Receive Communcation, Friend Request Basic Send, Pending split requests notification | Low | 2
Change Notification Source Settings | Toggle notification via Text/Email/Push notification Toggle notification suppression | Not Started | NO |  | Low | 2.5
Display Expense Statistics – Total Incoming, Outgoing, and Net Balance | Total incoming/outgoing expenses Total net balance (outgoing - incoming) | Not Started | NO | Expense Organization/History Basic View | Low | 4
Display Expense Statistics – Graphs for Net Balance over time | Graph of net balance over time | Not Started | NO | Expense Organization/History Basic View | Low | 4
Display Expense Statistics – View statistics for each payment category | View expense statistics for each category (food, rent, trips, other) | Not Started | NO | Expense Organization/History Basic View, Split Creation Options | Low | 4
Pending split requests notification | Show indicator when there are pending split requests | Not Started | NO | Split Creation Basic Send Communcation, Split Creation Basic Receive Communcation | Medium | 2
70.75